## Siraj Task Checklist
سراج (Siraj) — Day-by-Day Hackathon Task Checklist
Day | Hour Block | Assigned Member | Task Title | Description | Deliverables | Status
Day 1 | Hours 1-8 | Member 3 (BE) | Initialize Git Repository | Initialize Git repository, configure .gitignore, and share access with the team. | Shared Git repository | Not Started
Day 1 | Hours 1-8 | Member 1 (TL) | Architecture & Base Templates | Configure Vite/FastAPI templates, define CORS rules, and document API contracts. | Base templates, API contracts | Not Started
Day 1 | Hours 1-8 | Member 2 (FE) | Core Layout & Typography | Build dashboard frame, right-side RTL navigation sidebar, and index.css with design tokens. | Standard UI structure | Not Started
Day 1 | Hours 1-8 | Member 3 (BE) | Database Setup & Models | Set up SQLite with SQLAlchemy. Define tables for Users, Transactions, Budgets, Savings, and Alerts. | Database models | Not Started
Day 1 | Hours 1-8 | Member 4 (AI) | 3-Year Seed Data Engine | Implement seed.py with 36 months of realistic transactions for Sara (15k salary, summer vacation, Eid expenses, etc.). | Seeded database | Not Started
Day 1 | Hours 1-8 | Member 5 (Demo) | Persona & Scenario Script | Define the exact user walkthrough script (e.g., Sara tracking expense spikes, asking Siraj to set a coffee budget). | Written User Scenario Script | Not Started
Day 1 | Hours 9-24 | Member 1 (TL) | Routing & Auth | Implement JWT auth routes on BE and link them to FE layout. Build helper dashboard aggregators. | /auth endpoints & hooks | Not Started
Day 1 | Hours 9-24 | Member 2 (FE) | Pages & Recharts | Build Home/Dashboard (charts), Transactions, Alerts, and Chat pages using the local Mock API. | Interactive frontend shell | Not Started
Day 1 | Hours 9-24 | Member 3 (BE) | CRUD Endpoints | Write FastAPI routes for transaction list, custom budgets, savings goals progress, and financing status. | Complete CRUD API | Not Started
Day 1 | Hours 9-24 | Member 4 (AI) | Agent Prompts & Tools | Code the 15 system tools for the Gemini model. Develop SSE streaming response loops. | /chat stream API | Not Started
Day 1 | Hours 9-24 | Member 5 (Demo) | Script Reading & Visual Prep | Screen record prototype UI pages, check Arabic translations accuracy, write speech slides, and record voiceover draft. | Draft presentation slides | Not Started
Day 2 | Hours 25-36 | Member 1 (TL) | End-to-End Integration | Disable Frontend Mock API toggle. Wire Axios clients and EventSource loops to live FastAPI URLs. | Integrated Application | Not Started
Day 2 | Hours 25-36 | Member 2 (FE) | UI Polishing & Bugs | Implement micro-animations, loading state skeletons, Arabic numbers formatting, and fix layout bugs. | Polished Front-end | Not Started
Day 2 | Hours 25-36 | Member 3 (BE) | Performance & Diagnostics | Optimize SQL queries, write database connection error fallbacks, and check data integrity. | High-performance API | Not Started
Day 2 | Hours 25-36 | Member 4 (AI) | Agent Tuning & Guardrails | Refine Gemini system prompts to prevent Hallucinations. Test financial tools behavior on edge cases. | Bulletproof AI system | Not Started
Day 2 | Hours 25-36 | Member 5 (Demo) | Verification & Trial Runs | Run full workflow matching the script. Verify data state changes (e.g., adding coffee adds to chart immediately). | Verified workflow logs | Not Started
Day 2 | Hours 37-48 | Member 1 (TL) | Final Production Deploy | Deploy FastAPI backend to Render/Fly.io and React frontend to Vercel/Netlify. Verify HTTPS. | Live URL links | Not Started
Day 2 | Hours 37-48 | Member 2 (FE) | Deployment Polish | Coordinate with TL to verify the production build assets, routing, and favicon display. | Deployed Front-end | Not Started
Day 2 | Hours 37-48 | Member 3 (BE) | DB backup / Migrations | Lock SQLite production DB and double check seed data on production host. | Live DB instances | Not Started
Day 2 | Hours 37-48 | Member 4 (AI) | API Keys & Logs | Monitor production server logs to ensure AI requests execute smoothly under load. | Production-ready AI | Not Started
Day 2 | Hours 37-48 | Member 5 (Demo) | Final Video & Voiceover | Record high-quality screen video executing the user scenario. Sync voiceover script. Deliver final pitch video. | Final Video Pitch & Script | Not Started